## Tool Overview
Value Based Payment (VBP) Milestone Grid Overview
Value-Based Purchasing (VBP) is an approach that ties payment to the quality and efficiency of healthcare services delivered. This VBP milestone grid is a visual representation of key milestones and action steps in preparing an organization for operating under a value based payment arrangement. This tool may be helpful leadership teams, project managers, and other stakeholders track and manage the organization’s progress by providing a clear overview of important activities. Twelve key milestones have been identified and each tab on this Excel sheet covers the activities associated with a particular key milestone. These lists are not exhaustive of all activities/actions steps, and organizations are encouraged to add activities that are unique to your needs. Preparing to transition to VBP requires taking a comprehensive look at all aspects of organizational strategy and operations. We recommend establishing a VBP Transition Committee and using these milestones to develop a workplan with corresponding dates, responsibly staff and status checks.
Key Milestones
Milestone 1: Leadership and Board Engagement
Milestone 2: Staff Readiness
Milestone 3: Market Assessment
Milestone 4: Agreements/Partnerships
Milestone 5: Access and Capacity
Milestone 6: Quality Measurement/Data Monitoring
Milestone 7: Provider Alerts, Decision Support Tools and Registries
Milestone 8: Care Management
Milestone 9: Providing Person-Centered Care
Milestone 10: Behavioral Health/Primary Care Integration of Services
Milestone 11: Financial/Operational
Milestone 12: Demonstration of Organizational Financial Strength
Copyright © 2023 Health Management Associates, Inc.

## Leadership and Board Engagement
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 1: Leadership and Board Engagement
Activity | Comments
Take and review a VBP Readiness Assessment as a leadership team
Based on your assessment results, identify top three initiatives needed to ensure success and your related short, medium and long term goals
Assess the level at which leadership is committed and has the capacity to ensuring your organization succeeds in value-based payment contracts
Establish a VBP Leadership Team with representation from finance, clinical, operations and data analytics
Develop an overall value proposition for your organization that describes your unique strengths and service lines and if possible, should include outcomes data related to anticipated alternative payment arrangements (APM)
Provide VBP Leadership Team access to a performance management dashboard that enables it to monitor and respond to critical organizational indicators in real time. At a minimum include trends in membership by plan, quality outcomes for metrics with financial implications, utilization and cost with benchmarking
Assess familiarity with any of the quality metrics and performance targets included in existing contracts or for those contracts are not in place, those commonly used by payers for advanced APMs in your service area
Develop a list of performance metrics that should be tracked for desired APMs but are not being currently measured
Establish a performance indicator related to individual/client engagement that the organization's leadership is tracking on a regular basis
Assess ability to benchmark your performance
Assess adequacy of a strategic plan to enhance VBP-related performance
Assess progress being made in that strategic plan
Establish a process for your management team regularly track the results of individual/client experience survey
Engage in a comprehensive strategic planning process with your Board and other key stakeholders that prepares for the transition to value-based payments while maintaining fidelity to your organization's mission, vision and values
Determine the level of risk your organization is willing to take in relation to value-based payment through a process that includes executive leadership and members of the governing Board
Determine organizational risk tolerance: Conduct an assessment of market expectations for assuming financial risk contracts, gaps in practice panel size, HIT capabilities, operational readiness and reserves required to compete in that market; copy of risk mitigation strategy including assessment of partnership opportunities to address those gaps
Develop a financial plan that estimates cost of new investment in staff and infrastructure needed to pursue VBP and plan for securing those resources
Determine the adequacy of financial reserves required to assume that level of risk

## Staff Readiness
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 2: Staff Readiness
Activity | Comments
Assess administrative and clinical leadership knowledge about VBP
Assess direct service and other staff knowledge about VBP
Identify and enable a VBP clinical and operational champion who will serve as a "first level leader" and resource to direct care staff
Assure that staff within your organization understand the payor contracts/reimbursement system your organization has
Assess clinical staff preparedness to change their practice patterns (if necessary) to ensure your organization succeeds in value-based payment contracts
Develop and implement a strategic plan to enhance VBP-related performance and revenue
Determine areas where additional training is needed
Develop a staff training plan
Develop and implement a strategic plan to enhance VBP-related performance and revenue

## Market Assessment
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 3: Market Assessment
Activity | Comments
Assess your geographic coverage of the service area
Assess your market share in the service line for your line of business including being exclusive provider for any part of the market by geography or key service
Assess the range of alternative payment methodologies (APM) being offered by payer and insurance products in your service area
Review the expectations that payers or MCOs face regarding APM contracting (e.g., Medicaid expectations to increase that contracting in terms of prevalence or more advanced APMs)
Assess APMs you already have in place and the performance on those APMs
Conduct and analysis of APMs that other like service line providers in your market have in place

## Agreements and Partnerships
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 4: Agreements/Partnerships
Activity | Comments
Conduct an analysis to identify the other service providers in your community from whom the individuals you serve receive care
Establish formal written arrangements through an MOU, care compact or contract with social service providers:
Housing Providers/Services
Education/Schools
Child Welfare
Department of Corrections
Supported Employment Agencies
Establish formal written arrangements through an MOU, care compact or contract that enable the people you serve to access the entire range of behavioral health disorders:
Inpatient MH
IOP/PHP
Psych Rehab
Psychiatric Services
Crisis Services
SUD Detox
SUD Residential
SUD IOP/PHP
SUD Outpatient
MAT
Establish formal written arrangements through an MOU, care compact or contract with agreements with a full range of physical health providers:
Hospitals
Home Health
Skilled Nursing/Long-Term Care
Primary Care Providers
Dental Providers
Medical Specialists
Explore the feasibility of joining or creating a clinically integrated network of BH providers
Explore the feasibility of joining or creating a clinically integrated network that includes medical providers

## Access and Capacity
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 5: Access and Capacity
Access: Appointment availability for individual clients to complete needed intakes and assessments required to determine treatment needs Capacity: Staff and service availability for ongoing treatment determined necessary based on client assessment and treatment plan. Capacity implies the ability to add or decrease staff to ensure enough people to serve all individuals referred to the organization
Activity | Comments
Develop standard measures of access and performance targets
Measure your days to access care for intake/assessment on a quarterly basis
Measure your waiting times to getting a follow-up appointment after the initial intake/assessment by service type
Measure your days to access psychiatric availability on a quarterly basis
Track organizational performance to that standard and give feedback to clinicians on their access to care
Assess the value of providing outpatient services outside regular business hours for those clients who cannot be seen Monday through Friday 9 – 5
Assess the value of offering same day appointments for urgent AND non-urgent care
Offer 24/7 telephonic crisis response services
Offer phone nurse triage during and after operating hours
Assess the linguistic/cultural needs of the population in the service area
Insure adequate language translation/interpretation services available for non-English speaking individuals
Implement at minimum annual training of direct service and other staff on cultural competency
Staff fully mirror the cultural/linguistic demographics and/or experience of the community in the service area
Develop education materials, information on evaluation and assessments in multiple languages and at appropriate health literacy levels
Develop a outreach process for engaging new clients who have never been seen in your organization
Establish and track a performance indicator related to client engagement: Report on client engagement data over a period of 3+ months that at a minimum tracks portion of attributed members who are active clients in the practice

## Quality Measurement
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 6: Quality Measurement and Data Monitoring
Activity | Comments
Establish a Quality Improvement Team (QIT) composed of representatives of core departments including IT
Establish at least monthly QIT meetings
Develop a list of all measures tracked by your organization whether or not they are related to any current VBP contracts
Assess data sources and the timeliness and completeness of those data sources; develop a plan to address data source gaps
Establish the technology to support retrieving, storing, calculating and reporting out on clinical quality metrics
Outline the metrics you report on and your quality improvement processes
Set performance targets with a justification including benchmarking when possible
Identify which metrics have direct and which have indirect financial implications in the VBP contracts
Estimate the financial implications of meeting or missing performance targets
Review quality/outcome measure performance with clinical/programmatic leadership and direct service staff monthly
Establish a CQI plan for each key metric including a financial ROI analysis for making additional investments
Develop a strategy for using the data collected to improve clinical care and outcomes (e.g., utilize quality reports/data to determine highest utilizers and inform individual/client outreach when appropriate)
Develop a system to collect data on the social determinants of health outcomes of the people you are serving (e.g., housing status, employment status, criminal justice involvement)
Develop a report on the prevalence of key social determinants of health for your client population
Regularly assess the quality performance (not productivity) including unwarranted practice variation of individual clinicians and other team members within your organization
Consider tying quality and performance metrics to performance reviews, employee incentives or contractual expectations of employment

## Decision Support Tools
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 7: Provider Alerts, Decision Support Tools and Registries
Activity | Comments
Consider embedding evidenced-based clinical protocols and decision support tools electronically in your EHR or care management platform to aid in point-of-service decision making
Develop a system for direct service staff/care team members receive proactive alerts (e.g., via RHIOs) in your EHR for emergency room utilization and inpatient hospitalization
Establish a workflow to quickly act on data received regarding real-time admission, discharge and transfer (ADTs) alerts when your the individuals you serves are registered or discharged from the hospital and the emergency room
Develop a process to risk stratify your client population at the population level. [Note: risk stratification is a standardized process for determining all the clients in your population that fall into low, medium and high levels of risk]
Develop a standard timeframe for re-stratifying the population to ensure clients are receiving the most appropriate level of care
Develop a workflow to reach out to high risk individuals for ongoing follow up
Develop an actionable registry to monitor high risk individuals, including the date of their last appointment and the date and result of their last medication management visit (e.g., list of all individuals on antipsychotic medication, those with poor adherence with those medications, gaps in preventive or chronic disease management services, who have frequent ED use or hospital readmissions, recently discharged, recently left jail/prison, individuals experiencing their first episode of psychosis)

## Care Management
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 8: Care Management
Care Management: Behavioral Health Care Management encompasses the initial and ongoing assessment and monitoring aimed at medium and high risk behavioral health clients. Care management services include conducting outreach and engagement activities, completing health risk assessments, co-developing comprehensive care plans and coordination of communications across the continuum. Care Planning: A care plan is co-created with provider and client and enhances the treatment plan by customizing to specific client needs, diagnoses, preferences, medications and side effect management, and client-preferences to care across the health care delivery system
Activity | Comments
Assess payer (Medicaid agency or health plan) expectations for care management services
Identify potential funding sources for providing care management services
Determine if payers are delegating care management services to providers currently or are expected to do so in the future
Assess your current care management capabilities including if you were given a list of your most complex/high risk clients, do you feel your organization would have a model in place to manage that list (staffing, competency, capacity, and guidelines)?
Determine whether to offer care management services directly or through a relationship with an external partner
Assess required functionalities of your care management platform (intake of external data sources, integration with the EHR, assessment tools, risk stratification algorithms, care planning templates, task prioritization, transition of care workflows, ability to share care plans with the full interdisciplinary care team)
If the decision is made not to assume care management responsibilities, develop a plan with the external care management entity to gain access to their care plans for your patients
If the decision is made to assume care management responsibilities:
Determine whether to imbed an electronic care management system/platform as a source for the management of care
Consider having a staff person with a specific role (such as a care manager) to follow up routinely and frequently with clients that are deemed at higher risk than others
Develop a "common care plan" as a source for the management of care
Embed a Functional Assessment as part of the care plan process (ability to do tasks required to function independently)
Ensure that every direct service and other staff within the care team can collaborate on the development of a common care plan for particular individuals and work off this plan on an ongoing basis (e.g., read each other’s notes and collaborate in the maintenance and updates to plan)
Establish a protocol for conducting standard health risks and functional assessments captured as structured data in your care plan, EHR or other database/system
Track external referrals by referring provider and to which external provider an individuals is referred
Develop/build good relationships and processes with hospitals (e.g., hospital ED care navigators, discharge planners, coordinators) utilized by the individuals you serve for routine communications and handoffs
If you were given a list of your most complex/high risk clients, do you feel your organization would have a model in place to manage that list (staffing, competency, capacity, and guidelines)?
Develop a strategy to outreach to and engage any managed care members who are assigned to you but have never been seen in your behavioral health agency

## Providing Person-Centered Care
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 9: Providing Person-Centered Care
Activity | Comments
Determine the degree to which your clinical staff members are prepared to change their practice patterns to ensure your organization succeeds in value-based payment contracts?
Determine what clinical practice model changes you would make in order to succeed under an APM
Consider participating in or willing to participate in learning collaboratives with external providers to share experiences and best practices.
Train staff members to provide evidence-based care for the treatments of common mental health conditions, such as depression, anxiety, post-traumatic stress and substance use disorders
Implement a system for administering, tracking and reporting on industry-recognized measures (e.g., PHQ-9, GAD7, AUDIT-C)
Collect client satisfaction data through a survey tool. Report on client satisfaction data over a period of 3+ months and then demonstrate with minutes from your quality improvement committee that you are reviewing and addressing those findings
Develop a system for identifying and remediating top issues mentioned by clients
Provide use of an electronic portal for client and family access
Consider implementing person-centered tools, such as shared decision-making and decision support tools
Track visit cycle time (i.e. the amount of time it takes an individual from the time they enter the door to exit with a completed visit)
Establish a regular team meeting to discuss complicated or difficult cases
Provide clinicians with dashboards to inform them of their process and outcome metrics
Provide incentives for clinicians who meet performance standards tied to process and outcome measures
Create plans for formally engaging and communicating with physical health practices about mutual clients
Track outcomes of referrals from physical health providers

## Integrated Care
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 10: Integrated Care
Activity | Comments
Develop a culture of wellness across the organization
Create and implement an annual Health Risk Assessment on all persons served
Identify PCPs who provide care to a large segment of the population you serve or offer primary care services on-site
Develop a collaborative model of BHI with those PCPs that includes screening for individuals with BH conditions and prioritization of those individuals for referral whose BH conditions cannot be managed by the PCP
Explore the creation of models of care such as the use of telemedicine or co-location to offer integrated behavioral health services to PCP's patients in the most convenient fashion
Identify PCPs who provide care to a large segment of the population you serve
Establish collaborative relationships with PCP/Medical Specialty offices that supports routine and reciprocal communication
Assess the adequacy of your process for obtaining patient consent to share information with external members of the interdisciplinary care teams including SUD-related information
Develop plan to monitor collaboration and referral processes with main PCP/Medical Specialty offices
Establish a written agreement with key PCP practices whereby individuals can access same day care for urgent medical needs
Designate a staff person who will contact PCP offices and develop an ongoing relationship
Develop a communication tool to share information with PCPs at least every six months
Train clinical and case management staff to effectively plan for and support individuals' attendance to medical appointments
Determine capacity to collocate primary care services in the same physical facility in which individuals receive behavioral health services
Explore joint contracting with primary care providers for value-based payment arrangements

## Financial and Operational
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 11: Financial and Operational
Activity | Comments
Establish your cost per visit including non-CPT codable services (e.g. enabling services, social determinants of health)
Analyze cost per visit on a regular basis to identify cost efficiencies
Develop a cost-based charge structure and update annually
Calculate/monitor the total annual cost per client for in-house services
Consider utilizing Business Intelligence software to assimilate and report on data from internal systems (EHRs, billing systems, accounting systems), assimilate external claims data with internal data, manipulate third party claims data
Develop a revenue model to budget the amount and timing of revenue and cash flow of potential VBP arrangements
Evaluate the upfront costs of participating in the VBP arrangement and new skill sets/core competencies
Monitor direct service staff productivity including visits and RVUs (relative value units)
Train direct service staff on proper coding and documentation practices on a regular basis, at least annually
Consider whether to have professional coders on staff
Review the coding of direct service staff on a regular basis
Develop an incentive compensation program for direct and non-direct service staff including a provision for direct service staff productivity
Align your incentive program with existing quality incentive programs in payer contracts
Review productivity reports with clinical leadership and direct service staff
Monitor the productivity (panel size) of non-direct service staff
Monitor the utilization of specific services by individual for in-house services
Develop effective systems to monitor payer incentives
Meet with health plan representatives on a regular basis to review your performance on VBP arrangements

## Financial Strength
Copyright © 2023 Health Management Associates, Inc.
VBP Milestones DC Medicaid Business Transformation
Milestone 12: Demonstrating of Organizational Financial Strength
Activity | Comments
Establish more than 90 days of working capital. Definition: Days in Working Capital = (Current Assets - Current Liabilities)/(Total Annual Operating Expenses/365 days)
Evaluate reserve requirements and/or the opportunities to partner with other providers and/or assume a risk VBP contract
Maintain positive net assets for operations of at least 30 days
Prepare monthly financial statements and make the financials available within 15 business days of month end
Develop a service volume, profit and loss statement for each product with each health plan as well as a roll-up of all management care contracts
Present financials for approval by the board/finance committee each month
Develop a system where financials include a comparison to budget with a written explanation of variances and are prepared on the GAAP basis of accounting
Complete agency independent audit within six months of year end
Complete an independent audit for the past three years
Budget the amount and timing of revenue and cash flow of potential VBP arrangements
Evaluate reserve requirements and/or the opportunities to partner with other providers
Offer financial assistance to clients by subsidizing services based on client need as applicable
If applicable, review financial performance of any clinically integrated network that you participate in

## raw data (hidden)
Provider_Agency | Site | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | PANov | PADec | PAJan | PAFeb | PAMar | PAApr | PAMay | PAJun | PAJUL | PAAug | PASep | PAOct | PA2Total | PA2Met | OA1Nov | OA1DEc | OA1Jan | OA1Feb | OA1Mar | OA1Apr | OA1May | OA1Jun | OA1Jul | OA1Aug | OA1Sep | OA1Oct | OA2Nov | OA2Dec | OA2Jan | OA2Feb | OA2Mar | OA2Apr | OA2May | OA2Jun | OA2Jul | OA2Aug | OA2Sep | OA2OCt
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!